Selection of Project Target Area

- Overall Selection Approach

- Project Approach

In order to address the issue of the local community with the difficulty in accessing forest and water resource due to soil erosion caused by degradation of forest, the Project shall attempt to take an catchment based approach to reduce soil runoff from forest areas for conserving water resource in effective manner for the purpose of improvement of the quality of forest. In the project context, “catchment” shall be defined within the Project as forest area, wherein severe forest degradation and soil erosion have occurred, in identified Beats as the project implementation unit, which are the smallest forest administrative boundary.

- Oveall Selection

In the Project, while project target area is mainly territorial forest, Gomati Wildlife Sanctuary shall also target as project intervention area due to the significance of catchment area of Gomati Wildlife Sanctuary, which is taking water from Gomati and Khowai river catchment, wherein some areas are overly degraded by Jhum cultivation. Prior to the implementation of the Project, Beats have already been selected as per the selection process indicated below. Along with identification of Beats as project target area, District, Sub-Division as well as Range also have been identified. At the preparatory stage of the Project, JFMCs shall be selected from selected Beats based on Beat Forest Basic Plan.

In Gomati Wildlife Sanctuary, as all existing 27 JFMCs/EDCs (at the point of June 2018) shall be targeted in the Project, Beats as well as Ranges and Sub-Divisions of those JFMCs/EDCs shall be project target in order for the efficient and effective intervention. Thus, target JFMCs/EDCs in Gomati Wildlife Sanctuary have already been selected as the project target even prior to the initiation of the Project.

- Selection of Project Target Area

- Selection of Territorial Forest Area

  - Prioritization Criteria

For selection of Beats in territorial forest area, two major factors are examined: (1) land factors to enhance forest quality including current status of forest degradation and status of soil erosion and (2) socio-economic factors to alleviate poverty including status of RoFR, dependency on forest areas, and livelihood.

In the selection process of Beats, four major steps are introduced. They include (1) pre-shortlisting, (2) prioritization, (3) post-shortlisting, and (4) reducing the number of Beats due to the limitation of project budget. Throughout taking steps of (3) above, 144 Beats have been identified, and the number of Beats have been arrived 135 after step (4).

Table: Overall selection method for Beats

- Pre-shortlisting

- Remove Beats with open forest of less than 50 ha. - Remove Beats in Rowa Wildlife Sanctuary (WLS), Sepahijala WLS, and Trishna WLS Districts.

- Prioritization

- Rank Beats based on five criteria showing below.

- Post-shortlisting

- Remove ranges that consist of equal to or less than 2 eligible Beats. - Keep Beats within ranges that consist of equal to or less than 2 eligible Beats but with open forest area of greater than or equal to 150 ha.

- Reducing the number of Beats

- Remove lower ranked Beats due to the limitation of project budget.

For the prioritization of Beats, the following five criteria and their weights are used according to the degree of their significance for the project objectives.

| Criteria |  | Unit | Weight |
| --- | --- | --- | --- |
| Land factor |  |  |  |
| 1 | Current status of forest degradation (Ratio of areas classified as "Open Forest" or "Scrub" in legal forest to the total legal forest areas by Beat) | Percentage | 30% |
| 2 | Status of soil erosion (Ratio of areas classified as "Very Severe" or "Severe" to the total land areas by Beat) | Percentage | 25% |
| Socio-economic factor |  |  |  |
| 3 | RoFR (Ratio of the number of RoFR households to the total number of households by Beat) | Percentage | 15% |
| 4 | Dependency on forest (Ratio of households that do not own land to the total number of households by Beat) | Percentage | 10% |
| 5 | Livelihood (Ratio of households with casual labour as a source of income to the total number of households by Beat). | Percentage | 20% |

## *Source of Data:

## 1. Forest degradation (open forest and scrub) was provided by Forest Survey of India (FSI) as per its report made available in 2017. Shape file of forest Beat was supplied by TFD to FSI.

## 2. Data was provided by TSAC during the time of project formulation.

## 3. RoFR data was collected from the Forest Right Module of the data base maintained by Tripura Tribal Welfare Department (http://tsu.trp.nic.in) accessed in April 2018.

## 4. 5. Data pertaining to “Dependency on forest” in 4 and “Livelihood” in 5 was obtained from the website of socio economic and caste census, 2011 (secc.gov.in) maintained by Ministry of Rural Development, Government of India.

## Panchayat/Village Council wise population data was obtained from directorate of Panchayat. Government of Tripura were aggregated Beat wise on the basis of No.F.13(103)/For/Estt – 12/Part-II/37, 421-518 dated on 31st October 2014 read as No.F.13(03)/For/Estt – 12/Part-III/57009-92 date on 31st March, 2015.

## Data pertaining RoFR and SECC were also aggregated Beat wise as accurately as possible.

For each criterion, shortlisted Beats are scored by the following method below.

- Identify the maximum ratio and divide other ratios by the maximum ratio. Scores of all Beats become 100 or less (Normalized scores).

- Multiply the normalized scores calculated in Step 1 by weightage of each criterion. (Reduced scores)

- Sum up the reduced scores calculated in Step 2 and give priorities to Beats in descending order of the total scores.

- The Beats with higher scores will be selected as targets.

At the same time, below figure illustrates an example of scoring method for the Beat prioritization.

Figure: Example of scoring method for the Beat prioritization

  - Project Target Beats

Annex 1 shows a list of Beats selected based on the above-mentioned method.

- Gomati Wildlife Sanctuary

  - Prioritization of Project Target

In Gomati Wildlife Sanctuary, Beats of all existing JFMCs/EDCs shall be targeted for effective and efficient intervention of the Project. Currently, JFMCs are existing in the said area. However, as the function of those JFMCs is same as EDCs, the Project shall target on JFMCs as per the table below.

  - Project Target Area

The table below is showing the selected JFMCs/EDCs as well as Beats and Ranges in Gomati Wildlife Sanctuary.

| Name of Range | Name of Beat | Sl. No. | Name of JFMC/EDC | Name of Village | No of Families |
| --- | --- | --- | --- | --- | --- |
| Gandachara | Jagabandhu Para | 1 | Dalirai Para | Jagabandhupara | 42 |
|  |  | 2 | Balong humkarai |  | 62 |
|  | Gandachara Proper | 3 | Laxmipur EDC | Laxmipur | 50 |
|  |  | 4 | North Sarma | Gandachara | 25 |
|  |  | 5 | Matima Chakma | Pancharatan | 32 |
|  |  | 6 | Machkumbhir | Laxmipur | 28 |
|  |  | 7 | Khakchang | Ultachara | 36 |
|  | Dhalajari | 8 | Ramnagar EDC | Ramnagar | 51 |
|  |  | 9 | Sangrangma EDC |  | 48 |
|  | Ranipukur | 10 | Jarikusum | Sarma | 49 |
|  |  | 11 | Ranipukur EDC | Pancharatan | 50 |
|  | Ratannagar | 12 | NIL | NIL | 0 |
|  | Hatimatha | 13 | Hatimatha | Dalapati | 56 |
|  |  | 14 | Dalapati | Dalapati | 75 |
|  | Bhagirath Para | 15 | Mohinya para | Bhagirath Para | 70 |
|  |  | 16 | Dhanuram Para |  | 54 |
|  |  | 17 | Naba Kumar Para |  | 40 |
|  | Barabari | 18 | NIL | NIL | - |
| Raishyabari | Raishyabari Proper | 19 | Bowalkhali | Bowalkhali | 110 |
|  | Tuichakma | 20 | Thakurchara | Thakurchara | 54 |
|  |  | 21 | Chandidas Para | Tuichakma | 104 |
|  | Raima | 22 | Indrakishore | Raima | 60 |
|  |  | 23 | Khetradhan Roajapara |  | 35 |
|  | Potachara | 24 | Purba Potachara | Purba Potachara | 81 |
|  |  | 25 | Paschim Potachara | Paschim Potachara | 88 |
| Ganganagar | Ganganagar Proper | 26 | Ganganagar EDC | Ganganagar | 56 |
|  |  | 27 | Naithok EDC |  | 55 |
|  | Karmapara | 28 | Salpaha EDC | Karmapara | 37 |
|  | Karnamoni Para | 29 | Sisathai EDC | Karnamoni Para | 60 |
|  | Radharambari |  | NIL | NIL | 0 |
|  | Chakma para |  | NIL | NIL | 0 |
|  | Dangabari |  | NIL | NIL | 0 |