## Schedule
Attachment 05: Detailed Implementation Schedule
Detailed Implementation Schedule
| 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025 | [11 empty] | 2026 | [11 empty] | 2027 | [11 empty] | 2028
 | time axis 2018-04-01 to 2029-03-01
Component 1. Sustainable Forest Management
1.1 Department Mode
1.1.1 Improvement of Forest Nurseries
1.1.1.1 Hi-Tech Nursery
a) Construction of Nurseries
Establishment (Y1) | bar: 2019-05-01 to 2019-11-01
Maintenance work (Y2-Y5) | bar: 2019-12-01 to 2023-11-01
Recurrent work (Y2-Y5) | bar: 2019-12-01 to 2023-11-01
b) Seedling Production
1st Year Production and Maintenance and 2nd year maintenance (1st cycle from Y2) | 2019-12-01: 1; 2020-01-01: 1; 2020-02-01: 1; 2020-03-01: 1; 2020-04-01: 1; 2020-05-01: 1; 2020-06-01: 1; 2020-07-01: 1; 2020-08-01: 1; 2020-09-01: 1; 2020-10-01: 1; 2020-11-01: 1; 2020-12-01: 2; 2021-01-01: 2; 2021-02-01: 2; 2021-03-01: 2; 2021-04-01: 2; 2021-05-01: 2
1st Year Production and Maintenance and 2nd year maintenance (2nd cycle from Y3) | 2020-12-01: 1; 2021-01-01: 1; 2021-02-01: 1; 2021-03-01: 1; 2021-04-01: 1; 2021-05-01: 1; 2021-06-01: 1; 2021-07-01: 1; 2021-08-01: 1; 2021-09-01: 1; 2021-10-01: 1; 2021-11-01: 1; 2021-12-01: 2; 2022-01-01: 2; 2022-02-01: 2; 2022-03-01: 2; 2022-04-01: 2; 2022-05-01: 2
1st Year Production and Maintenance and 2nd year maintenance (3rd cycle from Y4) | 2021-12-01: 1; 2022-01-01: 1; 2022-02-01: 1; 2022-03-01: 1; 2022-04-01: 1; 2022-05-01: 1; 2022-06-01: 1; 2022-07-01: 1; 2022-08-01: 1; 2022-09-01: 1; 2022-10-01: 1; 2022-11-01: 1; 2022-12-01: 2; 2023-01-01: 2; 2023-02-01: 2; 2023-03-01: 2; 2023-04-01: 2; 2023-05-01: 2
1.1.1.2 Central Nursery
a) Improving Existing Central Nurseries | bar: 2019-08-01 to 2023-11-01
b) Seedling Production
1st Year Production and Maintenance and 2nd year maintenance (1st cycle from Y2) | 2019-12-01: 1; 2020-01-01: 1; 2020-02-01: 1; 2020-03-01: 1; 2020-04-01: 1; 2020-05-01: 1; 2020-06-01: 1; 2020-07-01: 1; 2020-08-01: 1; 2020-09-01: 1; 2020-10-01: 1; 2020-11-01: 1; 2020-12-01: 2; 2021-01-01: 2; 2021-02-01: 2; 2021-03-01: 2; 2021-04-01: 2; 2021-05-01: 2
1st Year Production and Maintenance and 2nd year maintenance (2nd cycle from Y3) | 2020-12-01: 1; 2021-01-01: 1; 2021-02-01: 1; 2021-03-01: 1; 2021-04-01: 1; 2021-05-01: 1; 2021-06-01: 1; 2021-07-01: 1; 2021-08-01: 1; 2021-09-01: 1; 2021-10-01: 1; 2021-11-01: 1; 2021-12-01: 2; 2022-01-01: 2; 2022-02-01: 2; 2022-03-01: 2; 2022-04-01: 2; 2022-05-01: 2
1st Year Production and Maintenance and 2nd year maintenance (3rd cycle from Y4) | 2021-12-01: 1; 2022-01-01: 1; 2022-02-01: 1; 2022-03-01: 1; 2022-04-01: 1; 2022-05-01: 1; 2022-06-01: 1; 2022-07-01: 1; 2022-08-01: 1; 2022-09-01: 1; 2022-10-01: 1; 2022-11-01: 1; 2022-12-01: 2; 2023-01-01: 2; 2023-02-01: 2; 2023-03-01: 2; 2023-04-01: 2; 2023-05-01: 2
1.1.2 Application of Plantation Models
1.1.2.1 Filter Strips & River bank Plantation
a) Filter Strip
1st cycle for 1st year Creation and Maintenance work and 2nd year maintenance work | 2020-12-01: 1; 2021-01-01: 1; 2021-02-01: 1; 2021-03-01: 1; 2021-04-01: 1; 2021-05-01: 1; 2021-06-01: 1; 2021-07-01: 1; 2021-08-01: 1; 2021-09-01: 1; 2021-10-01: 1; 2021-11-01: 1; 2021-12-01: 2; 2022-01-01: 2; 2022-02-01: 2; 2022-03-01: 2; 2022-04-01: 2; 2022-05-01: 2; 2022-06-01: 2; 2022-07-01: 2; 2022-08-01: 2; 2022-09-01: 2; 2022-10-01: 2; 2022-11-01: 2
2nd cycle for 1st year Creation and Maintenance work and 2nd year maintenance work | 2021-12-01: 1; 2022-01-01: 1; 2022-02-01: 1; 2022-03-01: 1; 2022-04-01: 1; 2022-05-01: 1; 2022-06-01: 1; 2022-07-01: 1; 2022-08-01: 1; 2022-09-01: 1; 2022-10-01: 1; 2022-11-01: 1; 2022-12-01: 2; 2023-01-01: 2; 2023-02-01: 2; 2023-03-01: 2; 2023-04-01: 2; 2023-05-01: 2; 2023-06-01: 2; 2023-07-01: 2; 2023-08-01: 2; 2023-09-01: 2; 2023-10-01: 2; 2023-11-01: 2
3rd cycle for 1st year Creation and Maintenance work and 2nd year maintenance work | 2022-12-01: 1; 2023-01-01: 1; 2023-02-01: 1; 2023-03-01: 1; 2023-04-01: 1; 2023-05-01: 1; 2023-06-01: 1; 2023-07-01: 1; 2023-08-01: 1; 2023-09-01: 1; 2023-10-01: 1; 2023-11-01: 1; 2023-12-01: 2; 2024-01-01: 2; 2024-02-01: 2; 2024-03-01: 2; 2024-04-01: 2; 2024-05-01: 2; 2024-06-01: 2; 2024-07-01: 2; 2024-08-01: 2; 2024-09-01: 2; 2024-10-01: 2; 2024-11-01: 2
b) River Bank Plantation
1 st cycle for 1st year Creation and Maintenance work and 2nd year maintenance work | 2020-12-01: 1; 2021-01-01: 1; 2021-02-01: 1; 2021-03-01: 1; 2021-04-01: 1; 2021-05-01: 1; 2021-06-01: 1; 2021-07-01: 1; 2021-08-01: 1; 2021-09-01: 1; 2021-10-01: 1; 2021-11-01: 1; 2021-12-01: 2; 2022-01-01: 2; 2022-02-01: 2; 2022-03-01: 2; 2022-04-01: 2; 2022-05-01: 2; 2022-06-01: 2; 2022-07-01: 2; 2022-08-01: 2; 2022-09-01: 2; 2022-10-01: 2; 2022-11-01: 2
2nd cycle for 1st year Creation and Maintenance work and 2nd year maintenance work | 2021-12-01: 1; 2022-01-01: 1; 2022-02-01: 1; 2022-03-01: 1; 2022-04-01: 1; 2022-05-01: 1; 2022-06-01: 1; 2022-07-01: 1; 2022-08-01: 1; 2022-09-01: 1; 2022-10-01: 1; 2022-11-01: 1; 2022-12-01: 2; 2023-01-01: 2; 2023-02-01: 2; 2023-03-01: 2; 2023-04-01: 2; 2023-05-01: 2; 2023-06-01: 2; 2023-07-01: 2; 2023-08-01: 2; 2023-09-01: 2; 2023-10-01: 2; 2023-11-01: 2
3rd cycle for 1st year Creation and Maintenance work and 2nd year maintenance work | 2022-12-01: 1; 2023-01-01: 1; 2023-02-01: 1; 2023-03-01: 1; 2023-04-01: 1; 2023-05-01: 1; 2023-06-01: 1; 2023-07-01: 1; 2023-08-01: 1; 2023-09-01: 1; 2023-10-01: 1; 2023-11-01: 1; 2023-12-01: 2; 2024-01-01: 2; 2024-02-01: 2; 2024-03-01: 2; 2024-04-01: 2; 2024-05-01: 2; 2024-06-01: 2; 2024-07-01: 2; 2024-08-01: 2; 2024-09-01: 2; 2024-10-01: 2; 2024-11-01: 2
c) Bandalling for 1st, 2nd and 3rd cycle | 2021-01-01: 1; 2021-02-01: 1; 2021-03-01: 1; 2022-01-01: 2; 2022-02-01: 2; 2022-03-01: 2; 2023-01-01: 3; 2023-02-01: 3; 2023-03-01: 3
1.1.3 Habitat Improvement in Gumti Sanctuary
1.1.3.1 Gumti Sanctuary
a) Fruit Trees Planting | bar: 2019-10-01; 2020-02-01 to 2020-04-01; 2020-10-01 to 2020-12-01; 2021-10-01 to 2021-12-01; 2022-10-01 to 2022-12-01; 2023-10-01 to 2023-12-01
b) Grassland Development | bar: 2020-10-01 to 2020-12-01; 2021-10-01 to 2021-12-01; 2022-10-01 to 2022-12-01
c) Weed (IAS) Eradication | bar: 2020-10-01 to 2020-12-01; 2021-10-01 to 2021-12-01; 2022-10-01 to 2022-12-01; 2023-10-01 to 2023-12-01; 2024-10-01 to 2024-12-01
d) Fire Line Making | bar: 2022-11-01 to 2023-03-01; 2024-02-01 to 2024-05-01; 2024-12-01 to 2025-03-01
e) Boundary Marking with Pillars | bar: 2019-06-01 to 2019-09-01; 2020-10-01 to 2020-12-01; 2021-11-01 to 2022-01-01
f) Construction/ Engineering Works
1) Check Dams - Earthen | bar: 2021-01-01 to 2021-03-01; 2022-01-01 to 2022-03-01; 2023-01-01 to 2023-03-01
2) Gully Plugging | bar: 2021-01-01 to 2021-03-01; 2022-01-01 to 2022-03-01; 2023-01-01 to 2023-03-01
3) Check Post and Guard Room | bar: 2020-09-01 to 2020-11-01
1.2 JFM Mode (by JFMC/ EDC)
1.2.1 Establishment of Decentralized People's Nursery
1.2.1.1 New JFMC/ EDC Nurseries (1st batch)
a) Establishment (Y2) (1st batch) | bar: 2019-12-01 to 2020-05-01
b) Seedling Production (1st batch)
Seedling Production (1st cycle from Y3)
First Year Production and Maintenance | bar: 2020-12-01 to 2021-11-01
Second Year Maintenance | bar: 2021-12-01 to 2022-05-01
Seedling Production (2nd cycle from Y4)
First Year Production and Maintenance | bar: 2021-12-01 to 2022-11-01
Second Year Maintenance | bar: 2022-12-01 to 2023-05-01
Seedling Production (3rd cycle from Y5)
First Year Production and Maintenance | bar: 2022-12-01 to 2023-11-01
Second Year Maintenance | bar: 2023-12-01 to 2024-05-01
1.2.1.2 New JFMC/ EDC Nurseries (2nd batch)
a) Establishment (Y3) (2nd batch) | bar: 2020-12-01 to 2021-05-01
b) Seedling Production (2nd batch)
Seedling Production (1st cycle from Y4)
First Year Production and Maintenance | bar: 2021-12-01 to 2022-11-01
Second Year Maintenance | bar: 2022-12-01 to 2023-05-01
Seedling Production (2nd cycle from Y5)
First Year Production and Maintenance | bar: 2022-12-01 to 2023-11-01
Second Year Maintenance | bar: 2023-12-01 to 2024-05-01
Seedling Production (3rd cycle from Y7)
First Year Production and Maintenance | bar: 2023-12-01 to 2024-11-01
Second Year Maintenance | bar: 2024-12-01 to 2025-05-01
1.2.1.3 New JFMC/ EDC Nurseries (3rd batch)
a) Establishment (Y4) (3rd batch) | bar: 2021-12-01 to 2022-05-01
b) Seedling Production (3rd batch)
Seedling Production (1st cycle from Y5)
First Year Production and Maintenance | bar: 2022-12-01 to 2023-11-01
Second Year Maintenance | bar: 2023-12-01 to 2024-05-01
Seedling Production (2nd cycle from Y6)
First Year Production and Maintenance | bar: 2023-12-01 to 2024-11-01
Second Year Maintenance | bar: 2024-12-01 to 2025-05-01
Seedling Production (3rd cycle from Y8)
First Year Production and Maintenance | bar: 2024-12-01 to 2025-11-01
Second Year Maintenance | bar: 2025-12-01 to 2026-05-01
1.2.2 Application of Plantation Models
1.2.2.1 Artificial Regeneration (AR) on Shifting Cultivation Areas
a-1) AR mixed (1st cycle)
1st year Creation and Maintenance work, 2nd, 3rd, 4th and 5th year maintenance work | 2020-12-01: 1; 2021-01-01: 1; 2021-02-01: 1; 2021-03-01: 1; 2021-04-01: 1; 2021-05-01: 1; 2021-06-01: 1; 2021-07-01: 1; 2021-08-01: 1; 2021-09-01: 1; 2021-10-01: 1; 2021-11-01: 1; 2021-12-01: 2; 2022-01-01: 2; 2022-02-01: 2; 2022-03-01: 2; 2022-04-01: 2; 2022-05-01: 2; 2022-06-01: 2; 2022-07-01: 2; 2022-08-01: 2; 2022-09-01: 2; 2022-10-01: 2; 2022-11-01: 2; 2022-12-01: 3; 2023-01-01: 3; 2023-02-01: 3; 2023-03-01: 3; 2023-04-01: 3; 2023-05-01: 3; 2023-06-01: 3; 2023-07-01: 3; 2023-08-01: 3; 2023-09-01: 3; 2023-10-01: 3; 2023-11-01: 3; 2023-12-01: 4; 2024-01-01: 4; 2024-02-01: 4; 2024-03-01: 4; 2024-04-01: 4; 2024-05-01: 4; 2024-06-01: 4; 2024-07-01: 4; 2024-08-01: 4; 2024-09-01: 4; 2024-10-01: 4; 2024-11-01: 4; 2024-12-01: 5; 2025-01-01: 5; 2025-02-01: 5; 2025-03-01: 5; 2025-04-01: 5; 2025-05-01: 5; 2025-06-01: 5; 2025-07-01: 5; 2025-08-01: 5; 2025-09-01: 5; 2025-10-01: 5; 2025-11-01: 5
a-2) AR Mixed (2nd cycle)
1st year Creation and Maintenance work, 2nd, 3rd, 4th and 5th year maintenance work | 2021-12-01: 1; 2022-01-01: 1; 2022-02-01: 1; 2022-03-01: 1; 2022-04-01: 1; 2022-05-01: 1; 2022-06-01: 1; 2022-07-01: 1; 2022-08-01: 1; 2022-09-01: 1; 2022-10-01: 1; 2022-11-01: 1; 2022-12-01: 2; 2023-01-01: 2; 2023-02-01: 2; 2023-03-01: 2; 2023-04-01: 2; 2023-05-01: 2; 2023-06-01: 2; 2023-07-01: 2; 2023-08-01: 2; 2023-09-01: 2; 2023-10-01: 2; 2023-11-01: 2; 2023-12-01: 3; 2024-01-01: 3; 2024-02-01: 3; 2024-03-01: 3; 2024-04-01: 3; 2024-05-01: 3; 2024-06-01: 3; 2024-07-01: 3; 2024-08-01: 3; 2024-09-01: 3; 2024-10-01: 3; 2024-11-01: 3; 2024-12-01: 4; 2025-01-01: 4; 2025-02-01: 4; 2025-03-01: 4; 2025-04-01: 4; 2025-05-01: 4; 2025-06-01: 4; 2025-07-01: 4; 2025-08-01: 4; 2025-09-01: 4; 2025-10-01: 4; 2025-11-01: 4; 2025-12-01: 5; 2026-01-01: 5; 2026-02-01: 5; 2026-03-01: 5; 2026-04-01: 5; 2026-05-01: 5; 2026-06-01: 5; 2026-07-01: 5; 2026-08-01: 5; 2026-09-01: 5; 2026-10-01: 5; 2026-11-01: 5
a-3) AR Mixed (3rd cycle)
1st year Creation and Maintenance work, 2nd, 3rd, 4th and 5th year maintenance work | 2022-12-01: 1; 2023-01-01: 1; 2023-02-01: 1; 2023-03-01: 1; 2023-04-01: 1; 2023-05-01: 1; 2023-06-01: 1; 2023-07-01: 1; 2023-08-01: 1; 2023-09-01: 1; 2023-10-01: 1; 2023-11-01: 1; 2023-12-01: 2; 2024-01-01: 2; 2024-02-01: 2; 2024-03-01: 2; 2024-04-01: 2; 2024-05-01: 2; 2024-06-01: 2; 2024-07-01: 2; 2024-08-01: 2; 2024-09-01: 2; 2024-10-01: 2; 2024-11-01: 2; 2024-12-01: 3; 2025-01-01: 3; 2025-02-01: 3; 2025-03-01: 3; 2025-04-01: 3; 2025-05-01: 3; 2025-06-01: 3; 2025-07-01: 3; 2025-08-01: 3; 2025-09-01: 3; 2025-10-01: 3; 2025-11-01: 3; 2025-12-01: 4; 2026-01-01: 4; 2026-02-01: 4; 2026-03-01: 4; 2026-04-01: 4; 2026-05-01: 4; 2026-06-01: 4; 2026-07-01: 4; 2026-08-01: 4; 2026-09-01: 4; 2026-10-01: 4; 2026-11-01: 4; 2026-12-01: 5; 2027-01-01: 5; 2027-02-01: 5; 2027-03-01: 5; 2027-04-01: 5; 2027-05-01: 5; 2027-06-01: 5; 2027-07-01: 5; 2027-08-01: 5; 2027-09-01: 5; 2027-10-01: 5; 2027-11-01: 5
b-1) AR Bamboo (1st cycle)
1st year Creation and Maintenance work, 2nd and 3rd year maintenance work | 2020-12-01: 1; 2021-01-01: 1; 2021-02-01: 1; 2021-03-01: 1; 2021-04-01: 1; 2021-05-01: 1; 2021-06-01: 1; 2021-07-01: 1; 2021-08-01: 1; 2021-09-01: 1; 2021-10-01: 1; 2021-11-01: 1; 2021-12-01: 2; 2022-01-01: 2; 2022-02-01: 2; 2022-03-01: 2; 2022-04-01: 2; 2022-05-01: 2; 2022-06-01: 2; 2022-07-01: 2; 2022-08-01: 2; 2022-09-01: 2; 2022-10-01: 2; 2022-11-01: 2; 2022-12-01: 3; 2023-01-01: 3; 2023-02-01: 3; 2023-03-01: 3; 2023-04-01: 3; 2023-05-01: 3; 2023-06-01: 3; 2023-07-01: 3; 2023-08-01: 3; 2023-09-01: 3; 2023-10-01: 3; 2023-11-01: 3
b-2) AR Bamboo (2nd cycle)
1st year Creation and Maintenance work, 2nd and 3rd year maintenance work | 2021-12-01: 1; 2022-01-01: 1; 2022-02-01: 1; 2022-03-01: 1; 2022-04-01: 1; 2022-05-01: 1; 2022-06-01: 1; 2022-07-01: 1; 2022-08-01: 1; 2022-09-01: 1; 2022-10-01: 1; 2022-11-01: 1; 2022-12-01: 2; 2023-01-01: 2; 2023-02-01: 2; 2023-03-01: 2; 2023-04-01: 2; 2023-05-01: 2; 2023-06-01: 2; 2023-07-01: 2; 2023-08-01: 2; 2023-09-01: 2; 2023-10-01: 2; 2023-11-01: 2; 2023-12-01: 3; 2024-01-01: 3; 2024-02-01: 3; 2024-03-01: 3; 2024-04-01: 3; 2024-05-01: 3; 2024-06-01: 3; 2024-07-01: 3; 2024-08-01: 3; 2024-09-01: 3; 2024-10-01: 3; 2024-11-01: 3
b-3) AR Bamboo (3rd cycle)
1st year Creation and Maintenance work, 2nd and 3rd year maintenance work | 2022-12-01: 1; 2023-01-01: 1; 2023-02-01: 1; 2023-03-01: 1; 2023-04-01: 1; 2023-05-01: 1; 2023-06-01: 1; 2023-07-01: 1; 2023-08-01: 1; 2023-09-01: 1; 2023-10-01: 1; 2023-11-01: 1; 2023-12-01: 2; 2024-01-01: 2; 2024-02-01: 2; 2024-03-01: 2; 2024-04-01: 2; 2024-05-01: 2; 2024-06-01: 2; 2024-07-01: 2; 2024-08-01: 2; 2024-09-01: 2; 2024-10-01: 2; 2024-11-01: 2; 2024-12-01: 3; 2025-01-01: 3; 2025-02-01: 3; 2025-03-01: 3; 2025-04-01: 3; 2025-05-01: 3; 2025-06-01: 3; 2025-07-01: 3; 2025-08-01: 3; 2025-09-01: 3; 2025-10-01: 3; 2025-11-01: 3
1.2.2.2 Aided Natural Regeneration (ANR) on Lower Catchment
a) ANR with 250 seedlings/ha gap plantation
a-1) ANR (mix & bamboo) (250 no/ha) (1st cycle)
1st year Creation and Maintenance work, 2nd and 3rd year maintenance work | 2020-12-01: 1; 2021-01-01: 1; 2021-02-01: 1; 2021-03-01: 1; 2021-04-01: 1; 2021-05-01: 1; 2021-06-01: 1; 2021-07-01: 1; 2021-08-01: 1; 2021-09-01: 1; 2021-10-01: 1; 2021-11-01: 1; 2021-12-01: 2; 2022-01-01: 2; 2022-02-01: 2; 2022-03-01: 2; 2022-04-01: 2; 2022-05-01: 2; 2022-06-01: 2; 2022-07-01: 2; 2022-08-01: 2; 2022-09-01: 2; 2022-10-01: 2; 2022-11-01: 2; 2022-12-01: 3; 2023-01-01: 3; 2023-02-01: 3; 2023-03-01: 3; 2023-04-01: 3; 2023-05-01: 3; 2023-06-01: 3; 2023-07-01: 3; 2023-08-01: 3; 2023-09-01: 3; 2023-10-01: 3; 2023-11-01: 3
a-2) ANR (mix & bamboo) (250 no/ha) (2nd cycle)
1st year Creation and Maintenance work, 2nd and 3rd year maintenance work | 2021-12-01: 1; 2022-01-01: 1; 2022-02-01: 1; 2022-03-01: 1; 2022-04-01: 1; 2022-05-01: 1; 2022-06-01: 1; 2022-07-01: 1; 2022-08-01: 1; 2022-09-01: 1; 2022-10-01: 1; 2022-11-01: 1; 2022-12-01: 2; 2023-01-01: 2; 2023-02-01: 2; 2023-03-01: 2; 2023-04-01: 2; 2023-05-01: 2; 2023-06-01: 2; 2023-07-01: 2; 2023-08-01: 2; 2023-09-01: 2; 2023-10-01: 2; 2023-11-01: 2; 2023-12-01: 3; 2024-01-01: 3; 2024-02-01: 3; 2024-03-01: 3; 2024-04-01: 3; 2024-05-01: 3; 2024-06-01: 3; 2024-07-01: 3; 2024-08-01: 3; 2024-09-01: 3; 2024-10-01: 3; 2024-11-01: 3
a-3) ANR (mix & bamboo) (250 no/ha) (3rd cycle)
1st year, 2nd and 3rd Creation and Maintenance work | 2022-12-01: 1; 2023-01-01: 1; 2023-02-01: 1; 2023-03-01: 1; 2023-04-01: 1; 2023-05-01: 1; 2023-06-01: 1; 2023-07-01: 1; 2023-08-01: 1; 2023-09-01: 1; 2023-10-01: 1; 2023-11-01: 1; 2023-12-01: 2; 2024-01-01: 2; 2024-02-01: 2; 2024-03-01: 2; 2024-04-01: 2; 2024-05-01: 2; 2024-06-01: 2; 2024-07-01: 2; 2024-08-01: 2; 2024-09-01: 2; 2024-10-01: 2; 2024-11-01: 2; 2024-12-01: 3; 2025-01-01: 3; 2025-02-01: 3; 2025-03-01: 3; 2025-04-01: 3; 2025-05-01: 3; 2025-06-01: 3; 2025-07-01: 3; 2025-08-01: 3; 2025-09-01: 3; 2025-10-01: 3; 2025-11-01: 3
1.2.2.3 Teak Plantation Management
a) Tree Species: 250 seedlings/ha gap plantation
1st year, 2nd and 3rd Creation and Maintenance work (1st cycle) | 2020-12-01: 1; 2021-01-01: 1; 2021-02-01: 1; 2021-03-01: 1; 2021-04-01: 1; 2021-05-01: 1; 2021-06-01: 1; 2021-07-01: 1; 2021-08-01: 1; 2021-09-01: 1; 2021-10-01: 1; 2021-11-01: 1; 2021-12-01: 2; 2022-01-01: 2; 2022-02-01: 2; 2022-03-01: 2; 2022-04-01: 2; 2022-05-01: 2; 2022-06-01: 2; 2022-07-01: 2; 2022-08-01: 2; 2022-09-01: 2; 2022-10-01: 2; 2022-11-01: 2; 2022-12-01: 3; 2023-01-01: 3; 2023-02-01: 3; 2023-03-01: 3; 2023-04-01: 3; 2023-05-01: 3; 2023-06-01: 3; 2023-07-01: 3; 2023-08-01: 3; 2023-09-01: 3; 2023-10-01: 3; 2023-11-01: 3
1st year, 2nd and 3rd Creation and Maintenance work (2nd cycle) | 2021-12-01: 1; 2022-01-01: 1; 2022-02-01: 1; 2022-03-01: 1; 2022-04-01: 1; 2022-05-01: 1; 2022-06-01: 1; 2022-07-01: 1; 2022-08-01: 1; 2022-09-01: 1; 2022-10-01: 1; 2022-11-01: 1; 2022-12-01: 2; 2023-01-01: 2; 2023-02-01: 2; 2023-03-01: 2; 2023-04-01: 2; 2023-05-01: 2; 2023-06-01: 2; 2023-07-01: 2; 2023-08-01: 2; 2023-09-01: 2; 2023-10-01: 2; 2023-11-01: 2; 2023-12-01: 3; 2024-01-01: 3; 2024-02-01: 3; 2024-03-01: 3; 2024-04-01: 3; 2024-05-01: 3; 2024-06-01: 3; 2024-07-01: 3; 2024-08-01: 3; 2024-09-01: 3; 2024-10-01: 3; 2024-11-01: 3
1st year, 2nd and 3rd Creation and Maintenance work (3rd cycle) | 2022-12-01: 1; 2023-01-01: 1; 2023-02-01: 1; 2023-03-01: 1; 2023-04-01: 1; 2023-05-01: 1; 2023-06-01: 1; 2023-07-01: 1; 2023-08-01: 1; 2023-09-01: 1; 2023-10-01: 1; 2023-11-01: 1; 2023-12-01: 2; 2024-01-01: 2; 2024-02-01: 2; 2024-03-01: 2; 2024-04-01: 2; 2024-05-01: 2; 2024-06-01: 2; 2024-07-01: 2; 2024-08-01: 2; 2024-09-01: 2; 2024-10-01: 2; 2024-11-01: 2; 2024-12-01: 3; 2025-01-01: 3; 2025-02-01: 3; 2025-03-01: 3; 2025-04-01: 3; 2025-05-01: 3; 2025-06-01: 3; 2025-07-01: 3; 2025-08-01: 3; 2025-09-01: 3; 2025-10-01: 3; 2025-11-01: 3
1.2.2.4 Silvi-Pastoral Plantation on Open Forests/ Grasslands
a) Model: 400 seedlings/ha gap plantation
1st year, 2nd, 3rd and 4h Creation and Maintenance work (1st cycle) | 2020-12-01: 1; 2021-01-01: 1; 2021-02-01: 1; 2021-03-01: 1; 2021-04-01: 1; 2021-05-01: 1; 2021-06-01: 1; 2021-07-01: 1; 2021-08-01: 1; 2021-09-01: 1; 2021-10-01: 1; 2021-11-01: 1; 2021-12-01: 2; 2022-01-01: 2; 2022-02-01: 2; 2022-03-01: 2; 2022-04-01: 2; 2022-05-01: 2; 2022-06-01: 2; 2022-07-01: 2; 2022-08-01: 2; 2022-09-01: 2; 2022-10-01: 2; 2022-11-01: 2; 2022-12-01: 3; 2023-01-01: 3; 2023-02-01: 3; 2023-03-01: 3; 2023-04-01: 3; 2023-05-01: 3; 2023-06-01: 3; 2023-07-01: 3; 2023-08-01: 3; 2023-09-01: 3; 2023-10-01: 3; 2023-11-01: 3; 2023-12-01: 4; 2024-01-01: 4; 2024-02-01: 4; 2024-03-01: 4; 2024-04-01: 4; 2024-05-01: 4; 2024-06-01: 4; 2024-07-01: 4; 2024-08-01: 4; 2024-09-01: 4; 2024-10-01: 4
1st year Creation and Maintenance work, 2nd, 3rd and 4th year maintenance work (2nd cycle) | 2021-12-01: 1; 2022-01-01: 1; 2022-02-01: 1; 2022-03-01: 1; 2022-04-01: 1; 2022-05-01: 1; 2022-06-01: 1; 2022-07-01: 1; 2022-08-01: 1; 2022-09-01: 1; 2022-10-01: 1; 2022-11-01: 1; 2022-12-01: 2; 2023-01-01: 2; 2023-02-01: 2; 2023-03-01: 2; 2023-04-01: 2; 2023-05-01: 2; 2023-06-01: 2; 2023-07-01: 2; 2023-08-01: 2; 2023-09-01: 2; 2023-10-01: 2; 2023-11-01: 2; 2023-12-01: 3; 2024-01-01: 3; 2024-02-01: 3; 2024-03-01: 3; 2024-04-01: 3; 2024-05-01: 3; 2024-06-01: 3; 2024-07-01: 3; 2024-08-01: 3; 2024-09-01: 3; 2024-10-01: 3; 2024-11-01: 3; 2024-12-01: 4; 2025-01-01: 4; 2025-02-01: 4; 2025-03-01: 4; 2025-04-01: 4; 2025-05-01: 4; 2025-06-01: 4; 2025-07-01: 4; 2025-08-01: 4; 2025-09-01: 4; 2025-10-01: 4; 2025-11-01: 4
1st year Creation and Maintenance work, 2nd, 3rd and 4th year maintenance work (3rd cycle) | 2022-12-01: 1; 2023-01-01: 1; 2023-02-01: 1; 2023-03-01: 1; 2023-04-01: 1; 2023-05-01: 1; 2023-06-01: 1; 2023-07-01: 1; 2023-08-01: 1; 2023-09-01: 1; 2023-10-01: 1; 2023-11-01: 1; 2023-12-01: 2; 2024-01-01: 2; 2024-02-01: 2; 2024-03-01: 2; 2024-04-01: 2; 2024-05-01: 2; 2024-06-01: 2; 2024-07-01: 2; 2024-08-01: 2; 2024-09-01: 2; 2024-10-01: 2; 2024-11-01: 2; 2024-12-01: 3; 2025-01-01: 3; 2025-02-01: 3; 2025-03-01: 3; 2025-04-01: 3; 2025-05-01: 3; 2025-06-01: 3; 2025-07-01: 3; 2025-08-01: 3; 2025-09-01: 3; 2025-10-01: 3; 2025-11-01: 3; 2025-12-01: 4; 2026-01-01: 4; 2026-02-01: 4; 2026-03-01: 4; 2026-04-01: 4; 2026-05-01: 4; 2026-06-01: 4; 2026-07-01: 4; 2026-08-01: 4; 2026-09-01: 4; 2026-10-01: 4; 2026-11-01: 4
1.2.3 Eco development
1.2.3.1 Identification of EDCs and Planning
a) Identification of EDC | bar: 2019-05-01 to 2019-06-01
b) Micro Planning | bar: 2019-10-01 to 2020-01-01
1.2.3.2 Eco development Activities
a) Revolving Fund to EDC for small IGAs | bar: 2020-04-01 to 2023-03-01
b) Entry point activities | bar: 2019-08-01 to 2019-11-01
Component 2. Soil and Moisture Conservation
2.1 Construction of Check Dams
a) Earthen Check-dam (Motel-I) | bar: 2020-10-01 to 2024-09-01
b) Earthen Check-dam (Motel-II) | bar: 2019-10-01 to 2023-09-01
c) RCC Check-dam (Motel-III) | bar: 2021-10-01 to 2024-09-01
2.2 Erosion Prevention Works combined with Check Dams
a) Brushwood Check-dam for Gully plugging | bar: 2020-10-01 to 2024-09-01
b) Contour Trenches | bar: 2020-10-01 to 2024-09-01
c) Mulching and Plantation around SMC works | bar: 2020-10-01 to 2024-09-01
2.3 Assessment of Soil and Moisture Conservation Model
a) Water Quality Monitoring | bar: 2022-01-01; 2022-07-01; 2023-01-01; 2023-07-01; 2024-01-01; 2024-07-01; 2025-01-01; 2025-07-01; 2026-01-01
Component 3. Livelihood Improvement
3.1 Objectives
3.2 Community Organizations for Livelihood Development
3.2.3 Trainings for SHGs/JLGs
a) Type I: Organizational Management and Accounting | bar: 2019-12-01 to 2023-08-01
b) Type II: Skill Development/ Technical Training | bar: 2020-01-01 to 2026-12-01
c) Type III: Marketing | bar: 2019-11-01 to 2024-02-01
3.3 NTFP based Livelihoods
3.3.3 Support to NTFP based Livelihoods
3.3.3.1 Support to NTFP Centre of Excellence (NCE) | bar: 2018-11-01 to 2023-03-01
3.3.3.2 Diagnostic Studies
a) NTFP Resource Assessment | bar: 2019-02-01 to 2020-01-01
3.3.3.3 Formation of NTFP Collectors Groups: Tier 3 (JFM mode) | bar: 2019-09-01 to 2022-08-01
3.3.3.4 Awareness Program on Sustainable Harvesting of NTFPs (Department Mode) | bar: 2019-04-01 to 2019-12-01
3.3.3.5 NTFP Collection/Primary Processing Centre: Tier 2 (Department Mode) | 2020-08-01: 1; 2020-09-01: 1; 2020-10-01: 1; 2020-11-01: 1; 2020-12-01: 1; 2021-01-01: 1; 2021-02-01: 1; 2021-03-01: 1; 2021-04-01: 1; 2021-05-01: 1; 2021-08-01: 2; 2021-09-01: 2; 2021-10-01: 2; 2021-11-01: 2; 2021-12-01: 2; 2022-01-01: 2; 2022-02-01: 2; 2022-03-01: 2; 2022-04-01: 2; 2022-05-01: 2; 2022-08-01: 3; 2022-09-01: 3; 2022-10-01: 3; 2022-11-01: 3; 2022-12-01: 3; 2023-01-01: 3; 2023-02-01: 3; 2023-03-01: 3; 2023-04-01: 3; 2023-05-01: 3
3.3.3.6 Advanced Processing and Value Addition Unit (APU): Tier 1
a) Diagnostic Study for Establishing Advance Level Processing and Value Addition Unit | bar: 2023-08-01 to 2023-12-01
b) Establishing Processing and Value Addition Unit | bar: 2024-01-01 to 2025-12-01
c) Promotion and Marketing Support | bar: 2024-04-01 to 2028-03-01
3.4 Agro-forestry based Livelihoods
3.4.1 Revising Agro-Forestry Models | bar: 2019-04-01 to 2020-03-01
3.4.2 Plantation of Agroforestry Crops
a) Plantation of Agroforestry Crops (605 tree saplings/ha on average)
1st batch (2021), 2nd batch (2022), 3rd batch (2023) | 2021-04-01: 1; 2021-05-01: 1; 2021-06-01: 1; 2021-07-01: 1; 2021-08-01: 1; 2021-09-01: 1; 2021-10-01: 1; 2021-11-01: 1; 2021-12-01: 1; 2022-01-01: 1; 2022-02-01: 1; 2022-03-01: 1; 2022-04-01: 2; 2022-05-01: 2; 2022-06-01: 2; 2022-07-01: 2; 2022-08-01: 2; 2022-09-01: 2; 2022-10-01: 2; 2022-11-01: 2; 2022-12-01: 2; 2023-01-01: 2; 2023-02-01: 2; 2023-03-01: 2; 2023-04-01: 3; 2023-05-01: 3; 2023-06-01: 3; 2023-07-01: 3; 2023-08-01: 3; 2023-09-01: 3; 2023-10-01: 3; 2023-11-01: 3; 2023-12-01: 3; 2024-01-01: 3; 2024-02-01: 3; 2024-03-01: 3
b) Follow up
1) Follow up support for 1st batch (2022) | bar: 2022-04-01 to 2025-03-01
2) Follow up support for 2nd batch (2023) | bar: 2023-04-01 to 2026-03-01
3) Follow up support for 3rd batch (2024) | bar: 2024-04-01 to 2027-03-01
3.4.3 Support for marketing
1) 1st batch SHG consortium grant (2024), 2nd batch (2025), 3rd batch (2026) | 2024-04-01: 1; 2024-05-01: 1; 2024-06-01: 1; 2024-07-01: 1; 2024-08-01: 1; 2024-09-01: 1; 2024-10-01: 1; 2024-11-01: 1; 2024-12-01: 1; 2025-01-01: 1; 2025-02-01: 1; 2025-03-01: 1; 2025-04-01: 2; 2025-05-01: 2; 2025-06-01: 2; 2025-07-01: 2; 2025-08-01: 2; 2025-09-01: 2; 2025-10-01: 2; 2025-11-01: 2; 2025-12-01: 2; 2026-01-01: 2; 2026-02-01: 2; 2026-03-01: 2; 2026-04-01: 3; 2026-05-01: 3; 2026-06-01: 3; 2026-07-01: 3; 2026-08-01: 3; 2026-09-01: 3; 2026-10-01: 3; 2026-11-01: 3; 2026-12-01: 3; 2027-01-01: 3; 2027-02-01: 3; 2027-03-01: 3
3.5 Livestock and Fish Farming based Livelihoods
3.5.1 Support for livestock farming | bar: 2020-04-01 to 2028-03-01
3.5.2 Support for fish farming | bar: 2020-04-01 to 2028-03-01
3.5.3 Support for marketing in livestock and fish farming | bar: 2021-04-01 to 2028-03-01
3.5.4 Support for training of para vet assistants | bar: 2020-04-01 to 2021-03-01
3.5.5 Organic Farming based Livelihoods
a) Support for setting-up model organic and conservation farms | bar: 2021-04-01 to 2027-03-01
3.5.6 Support for organic production and marketing | bar: 2021-04-01 to 2027-03-01
3.6 Ecotourism Development
3.6.1 Policy, strategic, institutional framework for streamlining ecotourism development
a) Review and Redrafting of Tripura Ecotourism Policy
1) Constitutive committee formation & expert appointment | bar: 2019-11-01
2) Public hearing and draft policy preparation | bar: 2019-12-01 to 2020-03-01
c) Establishment of Ecotourism Organization
1) Feasibility study | bar: 2020-02-01 to 2020-06-01
2) Preparation of an Organizational Manual for EDO | bar: 2020-02-01 to 2020-07-01
3) Ecotourism development fund | bar: 2020-08-01 to 2020-12-01
3.6.2 Promotion & Marketing of Ecotourism
a) Design and development of an ecotourism website | bar: 2021-10-01 to 2024-09-01
b) Publication and promotional materials | bar: 2021-10-01 to 2024-09-01
c) Assistance to participate travel trade fairs | bar: 2021-10-01 to 2024-09-01
3.6.3 Upgrading of Eco Parks
a) Construction / Engineering Works | bar: 2020-12-01 to 2021-11-01
b) Development of Programmes & Activity Modules | bar: 2021-08-01 to 2021-10-01
c) Staffing and Training | bar: 2021-10-01 to 2022-02-01
3.6.4 Support to existing ecotourism destinations (no cost) | bar: 2021-10-01 to 2022-09-01
3.6.5 Development of New ecotourism destination
a) Infrastructure development | bar: 2021-10-01 to 2022-08-01; 2022-10-01 to 2023-08-01; 2023-10-01 to 2024-08-01; 2024-10-01 to 2025-08-01
b) Non-infrastructure development | bar: 2021-10-01 to 2021-12-01; 2022-10-01 to 2022-12-01; 2023-10-01 to 2023-12-01; 2024-10-01 to 2024-12-01
3.7 Revolving Fund to JFMC/ EDC for small IGAs
3.7.3 Revolving Fund
a) Batch 1, Batch 2, Batch 3 | 2020-01-01: 1; 2020-02-01: 1; 2020-03-01: 1; 2020-04-01: 1; 2020-05-01: 1; 2020-06-01: 1; 2020-07-01: 1; 2020-08-01: 1; 2020-09-01: 1; 2020-10-01: 1; 2020-11-01: 1; 2020-12-01: 1; 2021-01-01: 2; 2021-02-01: 2; 2021-03-01: 2; 2021-04-01: 2; 2021-05-01: 2; 2021-06-01: 2; 2021-07-01: 2; 2021-08-01: 2; 2021-09-01: 2; 2021-10-01: 2; 2021-11-01: 2; 2021-12-01: 2; 2022-01-01: 3; 2022-02-01: 3; 2022-03-01: 3; 2022-04-01: 3; 2022-05-01: 3; 2022-06-01: 3; 2022-07-01: 3; 2022-08-01: 3; 2022-09-01: 3; 2022-10-01: 3; 2022-11-01: 3; 2022-12-01: 3
3.7.8 Grading and Rating of JFMCs/SHGs for IGA support
a) Grading and Rating | bar: 2021-03-01 to 2021-05-01; 2022-03-01 to 2022-05-01; 2023-03-01 to 2023-05-01
Component 4. Institutional Strengthening and Project Management
I. Institutional Strengthening
4.1 Department Mode
4.1.1 Infrastructure and Mobility Enhancement
4.1.1.1 Building Construction (3 Batches) | bar: 2019-10-01 to 2022-09-01
4.1.1.2 Vehicle Procurement (2 Batches) | bar: 2019-10-01 to 2021-09-01
4.1.2 Enhancement of GIS/ MIS facilities
4.1.2.1 Support for strengthening GIS/ MIS
a) Equipment | bar: 2019-04-01 to 2019-06-01; 2020-04-01 to 2020-05-01
b) Satellite imagery | bar: 2019-04-01 to 2019-06-01; 2021-04-01 to 2021-06-01; 2023-04-01 to 2023-06-01; 2025-04-01 to 2025-06-01
c) Human Resource (included in 4.3.1.1) | bar: 2019-04-01 to 2028-09-01
4.1.4 Gender Mainstreaming
a) Impact Study on Gender | bar: 2023-04-01 to 2023-06-01
4.1.5 Enhancement of Environment and Social Considerations
c) Institutional Framework for ESMSF/STFDPF | bar: 2022-01-01; 2022-07-01; 2023-01-01; 2023-07-01; 2024-01-01; 2024-07-01; 2025-01-01; 2025-07-01; 2026-01-01
f) Capacity Development for ESMSF/STFDPF Implementation (included in 4.1.5 and 4.2.2)
g) Biodiversity Assessment | bar: 2022-01-01; 2022-07-01; 2023-01-01; 2023-07-01; 2024-01-01; 2024-07-01; 2025-01-01; 2025-07-01; 2026-01-01
(Screening and Reporting) | bar: 2022-01-01; 2022-04-01; 2022-07-01; 2022-10-01; 2023-01-01; 2023-04-01; 2023-07-01; 2023-10-01; 2024-01-01; 2024-04-01; 2024-07-01; 2024-10-01; 2025-01-01; 2025-04-01; 2025-07-01; 2025-10-01; 2026-01-01
4.1.6 Capacity Development of Forest Department
4.1.6.1 Training
a) Training Plan Development - National | bar: 2020-04-01 to 2020-05-01; 2021-04-01 to 2021-05-01; 2022-04-01 to 2022-05-01; 2023-04-01 to 2023-05-01; 2024-04-01 to 2024-05-01; 2025-04-01 to 2025-05-01; 2026-04-01 to 2026-05-01
b) Training Plan Development - Overseas | bar: 2020-04-01 to 2020-05-01; 2021-04-01 to 2021-05-01; 2022-04-01 to 2022-05-01; 2023-04-01 to 2023-05-01; 2024-04-01 to 2024-05-01; 2025-04-01 to 2025-05-01; 2026-04-01 to 2026-05-01
c) Training: Skill Development, Managerial & Gender
i) PMU/ DMU/ SDMU
(A) Project Orientation | bar: 2019-04-01 to 2019-08-01
(B) Project orientation (Midterm) for new recruits | bar: 2024-04-01
(C) JFMC/EDC (I) | bar: 2019-09-01 to 2019-11-01; 2021-09-01 to 2021-11-01
(D) JFMC/EDC (II) | bar: 2020-10-01 to 2020-12-01; 2022-06-01 to 2022-08-01
(E) Micro planning and Annual Implementation plan | bar: 2020-02-01 to 2020-04-01; 2022-12-01 to 2023-02-01
(F) Project Management and M&E (I) | bar: 2019-12-01; 2020-06-01 to 2020-07-01
(G) Project Management and M&E (II) | bar: 2021-12-01 to 2022-02-01
(H) Gender Development | bar: 2019-10-01; 2020-05-01; 2020-09-01
(I) Organization Behavior and Communication | bar: 2020-10-01; 2021-01-01; 2021-03-01
(J) Design and Development of High-impact community based Ecotourism | bar: 2020-08-01; 2020-10-01; 2020-12-01
(K) JICA's Safeguard Policy | bar: 2019-04-01
(L) Ministerial Training | bar: 2019-08-01
(M) Emerging trends in biodiversity management | bar: 2021-02-01; 2022-03-01
(N) Basics og GIS (ToT mode) | bar: 2019-11-01
(O) Intermediate RS/GIS Training (ToT) | bar: 2021-05-01
(P) Thematic GIS/RS Training | bar: 2019-12-01; 2020-06-01; 2020-11-01; 2021-07-01
(Q) Database Training | bar: 2020-01-01; 2022-04-01
(R) Integration of GIS with MIS | bar: 2020-03-01
(S) GIS Training for Working Plan | bar: 2020-04-01
(T) Field Survey Training | bar: 2020-07-01
(U) Certificate course | bar: 2020-04-01 to 2020-06-01
(V) Basic MS Office and Internet Training | bar: 2019-09-01; 2021-01-01
(W) MIS training (Introductory) | bar: 2019-10-01 to 2019-11-01; 2021-10-01 to 2021-11-01
(X) Training on Plantation Management | bar: 2020-11-01 to 2021-08-01; 2023-05-01 to 2023-12-01
(Y) Training on Soil Moisture Conservation Technique | bar: 2020-08-01 to 2021-05-01; 2024-01-01 to 2024-09-01
ii) RMU
(A) Project Orientation | bar: 2019-10-01 to 2020-05-01
(B) Project orientation (Midterm) | bar: 2023-04-01 to 2023-09-01
(C) JFMC/EDC management | bar: 2019-11-01 to 2020-04-01; 2022-04-01 to 2022-09-01
(D) JFMC/EDC management | bar: 2019-10-01 to 2020-08-01; 2022-04-01 to 2022-12-01
(E) Community Organising ,Micro planning and Annual Implementation plan | bar: 2020-01-01 to 2021-06-01; 2023-04-01 to 2024-03-01
(F) Project Management and M&E | bar: 2020-10-01 to 2021-01-01; 2024-03-01 to 2024-06-01
(G) Gender Development | bar: 2019-10-01 to 2020-09-01; 2024-02-01 to 2025-01-01
(H) JFMC/EDC Management and Livelihood security (I) | bar: 2020-09-01 to 2021-04-01; 2023-04-01 to 2024-01-01
(I) JFMC/EDC Management and Livelihood security (II) | bar: 2022-01-01 to 2022-08-01; 2025-06-01 to 2026-04-01
(J) SHG formation and Strengthening for sustenance | bar: 2019-12-01 to 2020-01-01; 2023-02-01 to 2023-03-01
(K) ToT on IGAs | bar: 2020-03-01 to 2020-05-01; 2021-12-01 to 2022-02-01; 2023-11-01 to 2024-01-01; 2025-01-01 to 2025-03-01; 2026-10-01 to 2026-12-01
(L) Organization Behavior and Communication | bar: 2020-06-01 to 2021-09-01; 2022-04-01 to 2023-03-01; 2025-04-01 to 2026-01-01; 2026-04-01 to 2027-03-01
(M) Wild life management | bar: 2021-10-01 to 2023-03-01
(N) Basic MS office and internet | bar: 2020-06-01; 2022-06-01; 2024-06-01
(O) Data collection | bar: 2020-01-01 to 2020-10-01; 2024-04-01 to 2024-11-01
(P) MIS training (Introductory) | bar: 2020-08-01 to 2020-09-01; 2023-08-01 to 2023-09-01
(Q) Orientation on Concept of Safeguard | bar: 2020-01-01 to 2020-05-01
(R) Community facilitation and ESA | bar: 2020-08-01 to 2020-12-01
(S) Design and Development of High-impact community based Ecotourism | bar: 2021-02-01; 2024-03-01
(T) Training on Plantation Management | bar: 2020-01-01 to 2020-02-01; 2020-05-01 to 2020-08-01; 2021-01-01 to 2021-02-01; 2021-04-01; 2024-04-01; 2024-07-01 to 2024-10-01; 2025-01-01 to 2025-02-01; 2025-04-01
(U) Training on Soil Moisture Conservation Technique | bar: 2020-04-01 to 2020-05-01; 2020-11-01 to 2021-02-01; 2021-04-01 to 2021-05-01; 2023-12-01 to 2024-01-01; 2024-04-01 to 2024-07-01; 2024-11-01 to 2025-01-01
(V)Training for preparation of Beat action plan preparation | bar: 2019-12-01 to 2020-02-01; 2020-06-01 to 2020-08-01; 2021-10-01 to 2021-12-01; 2022-05-01 to 2022-07-01
d) Refresher Trainings
i) PMU/ DMU/ SDMU
(A) Refresher Training on Micro planning and Annual Implementation plan | bar: 2026-03-01 to 2026-04-01
(B) Refresher Training on Project Management and M&E | bar: 2025-08-01 to 2025-10-01
(C) Refresher Training on Gender Development | bar: 2022-11-01 to 2023-01-01
(D) Refresher Training on JICA's Safeguard Policy | bar: 2023-11-01; 2025-02-01
(E) Refresher Training on Ministerial Training | bar: 2024-04-01 to 2025-02-01
(F) Refresher Training on GIS Training for Working Plan | bar: 2023-11-01
(G) Refresher Training on MIS | bar: 2024-12-01 to 2025-01-01; 2026-07-01 to 2026-08-01
ii) RMU
(A) Refresher Training on JFMC/EDC management | bar: 2020-12-01 to 2021-05-01
(B) Refresher Training on Community Organising ,Micro planning and Annual Implementation plan | bar: 2021-06-01 to 2023-05-01
(C) Refresher Training on Gender Development | bar: 2022-04-01 to 2024-03-01
(D) Refresher Training on SHG formation and Strengthening for sustenance | bar: 2022-06-01 to 2022-07-01
(E) Refresher Training on MIS training | bar: 2021-09-01 to 2021-11-01; 2023-10-01 to 2023-12-01
(F) Refresher Training on Orientation on Concept of Safeguard | bar: 2022-06-01 to 2022-10-01
4.1.6.2 Exposure Visits
a) National/ Outside State
i) PMU/ DMU/ SDMU
(A) Exposure visit for PMU/DMU member (out side state) | bar: 2020-01-01 to 2020-02-01; 2020-04-01 to 2020-06-01; 2021-10-01 to 2022-01-01; 2022-10-01 to 2023-02-01; 2023-10-01 to 2024-02-01
ii) RMU
(A) Exposure visit for RMU member (out side state) | bar: 2020-07-01 to 2020-10-01; 2021-06-01 to 2021-09-01; 2022-07-01 to 2022-10-01; 2023-04-01 to 2023-07-01; 2024-06-01 to 2024-10-01; 2025-07-01 to 2025-10-01; 2026-07-01 to 2026-10-01; 2027-07-01 to 2027-10-01; 2028-04-01 to 2028-06-01
b) Overseas
(A) Exposure visit for PMU/DMU member (Overseas) | bar: 2021-01-01; 2022-02-01; 2023-01-01; 2024-01-01; 2025-01-01; 2026-01-01
4.1.7 Forest Research
a) Research on vegetative propagation technique of Bamboo | bar: 2020-10-01 to 2022-09-01
b) Research on vegetative propagation technique of Cane | bar: 2020-10-01 to 2022-09-01
c) Research on productivity of high value species | bar: 2020-10-01 to 2025-09-01
4.2 JFM Mode
4.2.1 Infrastructure support to Community Institutions
4.2.1.1 Building Construction
a) Multi Utility Centre (3 Batches) | bar: 2020-10-01 to 2021-01-01; 2021-10-01 to 2022-01-01; 2022-10-01 to 2023-01-01
4.2.2 Capacity Development of Community Institutions
4.2.2.1 Trainings
a) Training Skill Development Managerial and Gender
i) JFMC/ EDC Members
(A) Preparation of Micro Plan and Annual Implementation Plan | bar: 2019-10-01 to 2020-03-01; 2020-10-01 to 2021-03-01; 2021-10-01 to 2022-03-01
(B) JFMC/EDC Management ( Basic Course) | bar: 2020-04-01 to 2020-09-01; 2021-04-01 to 2021-09-01
(C ) JFMC/EDC Management ( Advance Course) | bar: 2022-04-01 to 2022-08-01; 2023-04-01 to 2023-08-01
(D) Training on Sustainable harvesting of NTFPs and Storing , Grading and marketing (Village level) | bar: 2019-11-01 to 2021-02-01; 2021-04-01 to 2022-02-01; 2022-04-01 to 2023-02-01; 2023-04-01 to 2024-02-01
(E ) Institutional Development Training for NTFP collectors | bar: 2020-10-01 to 2021-02-01; 2021-04-01 to 2022-02-01; 2022-04-01 to 2023-02-01; 2023-04-01 to 2024-02-01; 2024-04-01 to 2025-03-01
(F) Specialized training on Ecotourism (Basic) | bar: 2020-02-01 to 2020-06-01; 2021-10-01 to 2022-02-01; 2023-07-01 to 2023-11-01
(G) Specialized training on Eco Tourism ( Advanced) | bar: 2020-08-01 to 2021-02-01; 2021-10-01 to 2022-02-01; 2022-10-01 to 2023-01-01; 2024-02-01; 2024-04-01 to 2024-08-01; 2025-06-01 to 2025-09-01
(H) Awareness workshop on Basic agroforestry and IGAs (livestock, fisheries) | bar: 2020-01-01 to 2020-02-01; 2020-04-01 to 2021-02-01; 2021-04-01 to 2022-02-01; 2022-04-01 to 2023-02-01; 2023-04-01 to 2024-02-01; 2024-04-01 to 2025-02-01; 2025-04-01 to 2025-09-01
(I) One day awareness workshop on Organic Farming | bar: 2020-04-01 to 2021-02-01; 2021-04-01 to 2022-02-01; 2022-04-01 to 2023-02-01; 2023-04-01 to 2024-02-01; 2024-04-01 to 2025-02-01; 2025-04-01 to 2025-09-01
(J) Para-vet assistant residential training | bar: 2020-10-01 to 2020-12-01; 2022-11-01 to 2023-01-01
ii) SHG Members
(A)Group formation and internal saving | bar: 2019-08-01 to 2020-02-01; 2020-04-01 to 2021-02-01; 2022-01-01 to 2023-02-01; 2023-04-01 to 2023-11-01; 2024-08-01 to 2025-02-01; 2025-04-01 to 2026-01-01
(B) Business Planning | bar: 2019-12-01 to 2020-02-01; 2020-04-01 to 2021-06-01; 2022-01-01 to 2023-02-01; 2023-04-01 to 2023-07-01; 2024-04-01 to 2025-02-01
(C) IGA Specific training | bar: 2019-10-01 to 2020-02-01; 2020-04-01 to 2021-02-01; 2021-06-01 to 2022-02-01; 2022-06-01 to 2023-02-01; 2023-04-01 to 2023-12-01; 2024-04-01 to 2024-10-01; 2025-07-01 to 2026-03-01
(D) Community Facilitation and ESA for Environmental and Social Safeguard | bar: 2019-08-01 to 2020-02-01; 2020-04-01 to 2020-06-01; 2022-06-01 to 2023-02-01
(E) Awareness generation on project components | bar: 2019-08-01 to 2020-02-01; 2020-04-01 to 2020-08-01; 2022-09-01 to 2023-02-01; 2023-04-01 to 2023-10-01
(F) Value addition and Skill Development Training support to Mimi CCFCs | bar: 2020-01-01 to 2020-02-01; 2020-05-01 to 2021-02-01; 2021-05-01 to 2022-01-01; 2022-07-01 to 2023-01-01; 2023-08-01 to 2024-01-01; 2024-08-01 to 2024-12-01; 2025-08-01 to 2025-12-01; 2026-07-01 to 2026-12-01
b) Refresher Trainings
i) JFMC/ EDC Members
(A) Refreshers training on JFMC/EDC Management | bar: 2020-05-01 to 2021-02-01; 2021-06-01 to 2022-03-01; 2022-08-01 to 2023-05-01
(B) Refresher training on Sustainable harvesting of NTFPs | bar: 2021-01-01 to 2021-10-01; 2022-06-01 to 2023-03-01; 2023-09-01 to 2024-06-01
(C) Refresher training on Nurshury management | bar: 2021-11-01 to 2022-08-01; 2023-04-01 to 2024-01-01; 2024-08-01 to 2025-05-01
ii) SHG Members
(A) Refresher Training on Group formation and internal saving | bar: 2022-04-01 to 2023-02-01; 2024-04-01 to 2025-02-01
(B) Refresher Training on Business Planning | bar: 2022-08-01 to 2023-06-01; 2024-09-01 to 2025-07-01
(C) Refresher Training IGA Specific training | bar: 2023-04-01 to 2024-02-01; 2025-10-01 to 2026-08-01
4.2.2.2 Exposure Visit
a) National/ out side State
(A) Exposure visit for JFMC/EDC/SHG (out side state) | bar: 2020-04-01 to 2021-02-01; 2021-08-01 to 2022-06-01; 2025-06-01 to 2026-04-01; 2027-02-01 to 2027-12-01
b) Within State - Cross learning
(A) Exposure visit for JFMC/EDC/SHG (with in state) | bar: 2020-07-01 to 2021-05-01; 2022-07-01 to 2023-05-01; 2024-09-01 to 2025-07-01; 2026-10-01 to 2027-08-01
II. Project Management
4.3 Department Mode
4.3.1 Preparatory Activity for Project Implementation
4.3.1.1 Institutional Set-up and Procurement
a) Establishment of PMU/DMU/SDMU/RMU | bar: 2018-10-01 to 2019-01-01
b) Deployment/Hiring of Project Staff | bar: 2018-11-01 to 2028-09-01
c) Procurement of PMC | bar: 2018-10-01 to 2019-09-01
4.3.1.2 Map preparation
a) Hiring contractor for mapping | bar: 2019-02-01 to 2021-01-01
4.3.1.3 Batch-wise Approach
a) GB meeting (1st meeting) | bar: 2018-10-01
4.3.1.4 Preparation of Beat Forest Basic Plan (BFBP)
a) Year 1 | bar: 2019-05-01 to 2019-12-01
b) Year 2 | bar: 2019-10-01 to 2020-05-01
4.3.1.5 Baseline Surveys
a) Baseline Surveys | bar: 2019-08-01 to 2019-11-01
4.3.1.6 Identification of RoFR and JFMC lands
a) RoFR area | bar: 2019-01-01 to 2022-12-01
b) JFM area | bar: 2019-01-01 to 2022-12-01
4.3.1.7 Preparatory Activity for Community Mobilization & Planning
a) Modification/Development of Guidelines/manuals/Brochures | bar: 2018-10-01 to 2019-03-01; 2020-02-01 to 2020-03-01; 2022-02-01 to 2022-03-01; 2024-02-01 to 2024-03-01; 2026-02-01 to 2026-03-01; 2028-02-01 to 2028-03-01
b) Formation of DMU, SDMU and RMU | bar: 2018-10-01 to 2019-01-01
c) Recruitment of COs, LCs and FFs | bar: 2018-10-01 to 2019-01-01
4.3.1.8 Review and Revision of Project Manual
a) Operation Manual | bar: 2018-10-01 to 2019-03-01
b) Technical manuals/handbook | bar: 2019-04-01 to 2021-03-01
c) Orientation material | bar: 2019-02-01 to 2019-03-01
4.3.1.9 Orientation of Project Staff
a) PMU/DMU | bar: 2018-12-01
b) SDMU/RMU | bar: 2018-12-01 to 2019-02-01
4.3.2 Monitoring & Evaluation
4.3.2.1 Monitoring
a) Annual Planning & Review Workshop
i) PMU | bar: 2020-03-01; 2021-03-01; 2022-03-01; 2023-03-01; 2024-03-01; 2025-03-01; 2026-03-01; 2027-03-01; 2028-03-01
i) DMU | bar: 2020-02-01; 2021-02-01; 2022-02-01; 2023-02-01; 2024-02-01; 2025-02-01; 2026-02-01; 2027-02-01; 2028-02-01
b) Concurrent Monitoring and Review
i) HPSC - Twice a year | bar: 2018-10-01; 2019-05-01; 2019-12-01; 2020-05-01; 2020-12-01; 2021-05-01; 2021-12-01; 2022-05-01; 2022-12-01; 2023-05-01; 2023-12-01; 2024-05-01; 2024-12-01; 2025-05-01; 2025-12-01; 2026-05-01; 2026-12-01; 2027-05-01; 2027-12-01; 2028-09-01
ii) GB - Quarterly | bar: 2018-10-01; 2019-01-01; 2019-04-01; 2019-07-01; 2019-10-01; 2020-01-01; 2020-04-01; 2020-07-01; 2020-10-01; 2021-01-01; 2021-04-01; 2021-07-01; 2021-10-01; 2022-01-01; 2022-04-01; 2022-07-01; 2022-10-01; 2023-01-01; 2023-04-01; 2023-07-01; 2023-10-01; 2024-01-01; 2024-04-01; 2024-07-01; 2024-10-01; 2025-01-01; 2025-04-01; 2025-07-01; 2025-10-01; 2026-01-01; 2026-04-01; 2026-07-01; 2026-10-01; 2027-01-01; 2027-04-01; 2027-07-01; 2027-10-01; 2028-01-01; 2028-04-01; 2028-07-01
iii) EB - Monthly | bar: 2018-10-01 to 2028-09-01
iv) PMU - Monthly | bar: 2018-10-01 to 2028-09-01
v) DMU - Fortnightly | bar: 2018-10-01 to 2028-09-01
c) Computerized Accounting System | bar: 2018-10-01 to 2018-11-01; 2019-10-01; 2020-10-01; 2021-10-01; 2022-10-01; 2023-10-01; 2024-10-01; 2025-10-01; 2026-10-01; 2027-10-01
4.3.2.2 Impact Assessment & Studies
a) Socio-Economic Surveys
i) Baseline | bar: 2019-08-01 to 2019-11-01
ii) Mid-Term/ End-Term | bar: 2023-08-01 to 2023-11-01; 2028-02-01 to 2028-05-01
b) Bio-physical Surveys
Forest composition and biodiversity | bar: 2019-04-01 to 2019-06-01; 2025-08-01 to 2025-10-01; 2028-04-01 to 2028-06-01
Forest carbon stock study | bar: 2019-04-01 to 2019-07-01; 2022-04-01 to 2022-07-01; 2026-04-01 to 2026-07-01
Awareness on sustainable forest/water use | bar: 2019-10-01 to 2019-12-01; 2028-02-01 to 2028-04-01
c) Impact Assessment | bar: 2024-11-01 to 2025-02-01
d) Thematic Short Studies | bar: 2023-07-01 to 2023-09-01; 2026-07-01 to 2026-08-01
4.3.2.3 Annual Statutory Financial Audits
a) Annual Statutory Financial Audits | bar: 2020-04-01; 2021-04-01; 2022-04-01; 2023-04-01; 2024-04-01; 2025-04-01; 2026-04-01; 2027-04-01; 2028-04-01
4.3.2.4 Public Relations and Communication
a) Newsletter | bar: 2019-04-01; 2019-11-01; 2020-04-01; 2020-11-01; 2021-04-01; 2021-11-01; 2022-04-01; 2022-11-01; 2023-04-01; 2023-11-01; 2024-04-01; 2024-11-01; 2025-04-01; 2025-11-01; 2026-04-01; 2026-11-01; 2027-04-01; 2027-11-01
b) Brochures and leaflets | bar: 2019-02-01 to 2019-09-01; 2023-08-01 to 2023-10-01
c) Annual Report | bar: 2020-01-01; 2021-01-01; 2022-01-01; 2023-01-01; 2024-01-01; 2025-01-01; 2026-01-01; 2027-01-01; 2028-01-01
d) Website Development | bar: 2019-01-01 to 2019-03-01
4.3.3 Phase-Out Activity - Project
a) Preparation of Sustainability Plan | bar: 2025-10-01 to 2026-09-01
b) Transfer of Assets and Resources | bar: 2026-10-01 to 2028-09-01
4.4 JFM Mode
4.4.1 Preparatory Activity for Community Mobilization & Planning
4.4.1.1 Constitution/ Reconstitution of JFMC/ EDC for Batch 1, 2, 3 | 2019-10-01: 1; 2019-11-01: 1; 2019-12-01: 1; 2020-01-01: 1; 2020-02-01: 1; 2020-03-01: 1; 2020-10-01: 2; 2020-11-01: 2; 2020-12-01: 2; 2021-01-01: 2; 2021-02-01: 2; 2021-03-01: 2; 2021-10-01: 3; 2021-11-01: 3; 2021-12-01: 3; 2022-01-01: 3; 2022-02-01: 3; 2022-03-01: 3
4.4.1.3 Micro Planning
a) Baseline Survey | 2020-02-01: 1; 2020-03-01: 1; 2020-04-01: 1; 2021-02-01: 2; 2021-03-01: 2; 2021-04-01: 2; 2022-02-01: 3; 2022-03-01: 3; 2022-04-01: 3
b) Micro Plan Preparation for Batch 1, 2, 3 | 2020-04-01: 1; 2020-05-01: 1; 2020-06-01: 1; 2020-07-01: 1; 2020-08-01: 1; 2020-09-01: 1; 2021-04-01: 2; 2021-05-01: 2; 2021-06-01: 2; 2021-07-01: 2; 2021-08-01: 2; 2021-09-01: 2; 2022-04-01: 3; 2022-05-01: 3; 2022-06-01: 3; 2022-07-01: 3; 2022-08-01: 3; 2022-09-01: 3
4.4.2 Operationalizing M&E System
a) Annual Planning & Review Workshops
i) Batch 1 | bar: 2021-04-01; 2022-04-01; 2023-04-01; 2024-04-01
ii) Batch 2 | bar: 2022-04-01; 2023-04-01; 2024-04-01; 2025-04-01
iii) Batch 3 | bar: 2023-04-01; 2024-04-01; 2025-04-01; 2026-04-01
b) Annual Statutory Financial Audits
i) Batch 1 | bar: 2021-04-01; 2022-04-01; 2023-04-01; 2024-04-01
ii) Batch 2 | bar: 2022-04-01; 2023-04-01; 2024-04-01; 2025-04-01
iii) Batch 3 | bar: 2023-04-01; 2024-04-01; 2025-04-01; 2026-04-01
c) Annual Social Audits
i) Batch 1 | bar: 2021-04-01; 2022-04-01; 2023-04-01; 2024-04-01
ii) Batch 2 | bar: 2022-04-01; 2023-04-01; 2024-04-01; 2025-04-01
iii) Batch 3 | bar: 2023-04-01; 2024-04-01; 2025-04-01; 2026-04-01
4.4.3 Phase-Out Activity - JFM
a) Preparation of Sustainability Plan
a-1) Batch 1 | bar: 2025-04-01 to 2027-03-01
a-2) Batch 2 | bar: 2026-04-01 to 2028-03-01
a-3) Batch 3 | bar: 2027-04-01 to 2028-09-01
b) Transfer of Assets and Resources for Batch 1, 2, 3 | bar: 2027-04-01 to 2028-09-01
c) Revisiting and Revising Beat Action Plans for Batch 1, 2, 2 | bar: 2027-04-01 to 2028-09-01
Component 5. Consulting Service
Preparation of procurement | bar: 2018-09-01 to 2019-07-01
Consulting service | bar: 2019-08-01 to 2025-08-01