## Action Plan
Attachment 19: Time-Bound Action Plan
Time-Bound Action Plan
Area | Agreed Action | Responsible Person (Agency) | Target Date |  | Revised Date (as of ) | Actual Completion | Indicators
|  |  | Start | Complete
Policy Interventions | Registering NCE as autonomous entity | TFD |  | 2018-07-01 |  |  | Registration Certificate
| Employment Policy of Project Staff | TFD/ PMU | 2018-07-01 | 2018-09-01 |  |  | Notification
| NTFP Policy Finalization and Minimum Support Price (MSP) for NTFP | TFD/ PMU | 2018-10-01 | 2019-03-01 |  |  | Policy Notification
| Revision of JFM Rules/ Resolution | TFD/ PMU | 2018-10-01 | 2019-03-01 |  |  | Policy Notification
Institutional Arrangement | Budgetary Sanction including counterpart funding for FY 2018/19 | TFD/ PMU | 2018-07-01 | 2018-08-01 |  |  | Approval by State Gov.; and Budget release
| Nomination of PD | TFD | 2018-07-02 | 2018-08-01 |  |  | Government Order
| Constitution of High Power Steering Committee | PMU | 2018-07-03 | 2018-07-01 |  |  | Government Order
| Constitution of District Level Advisory Committee (DLAC) | PMU | 2018-08-01 | 2018-09-01 |  |  | Government Order
| Revised Memorandum of Association and bylaws | PMU | 2018-09-01 | 2018-09-01 |  |  | Document
| Constituting Governing Body and Executive Committee | TFD | 2018-09-01 | 2018-10-01 |  |  | Intimation to Registrar of the Societies
| Approval of MOA and bylaws of the Society by the Finance Department | TFD | 2018-09-01 | 2018-10-01 |  |  | Letter from Finance Deptt/file approval
| Issuance of GO for establishing PMU, DMU, SDMU and RMU functional | TFD/ PMU | 2018-10-01 | 2018-10-01 |  |  | Government Order
| Notification for deputation of Staff to PMU from FD and Other Departments | HPSC | 2018-10-01 | 2018-01-01 |  |  | Notification
| Deployment of TFD staff to DMU/SDMU and RMU | TFD | 2018-11-01 | 2018-12-01 |  |  | Office Order PCCF, TFD
| Deputation of Staff from Other Departments | GoT | 2018-11-01 | 2018-12-01 |  |  | Government Order
| Preparation of Annual Plan and Allocation of annual budget for FY2019/20 | HPSC | 2019-03-01 | 2019-04-01 |  |  | Budget Release Order
| Establishing GIS and MIS systems | PMU | 2019-04-01 | 2019-09-01 |  |  | Maps and Reports
| Establishing Computerized Financial Management and Accounting System | PMU | 2019-04-01 | 2019-09-01 |  |  | Computerized SOE
Consulting Services | REOI announcement | PMU | 2018-08-01 | 2018-09-01 |  |  | EOI Notice
| EOI Evaluation | PMU | 2018-09-01 | 2018-10-01
| Request for Concurrence of TOR, Short-list, L/I to JICA New Delhi Office | PMU | 2018-09-01 | 2018-09-01 |  |  | Request Letter by PMU
| JICA's Concurrence to TOR, Short-list, and L/I | JICA | 2018-10-01 | 2018-10-01 |  |  | No Objection Letter by JICA
| Issuance of L/I to Short-listed Consultants | PMU | 2018-11-01 | 2018-11-01 |  |  | L/I
| Technical Bid Evaluation | PMU | 2019-01-01 | 2019-01-01
| Request for JICA's Concurrence to Evaluation Results of Proposals | PMU | 2019-06-01 | 2019-02-01 |  |  | Request Letter by PMU
| JICA's Concurrence to Evaluation Results | JICA | 2019-02-01 | 2019-02-01 |  |  | No Objection Letter by JICA
| Contract negotiation with the consultants | PMU | 2019-04-01 | 2019-05-01 |  |  | Contract Documents
| JICA's concurrence for contract signing | JICA | 2019-05-01 | 2019-06-01 |  |  | Notice to Proceed/ Commencement Order by PMU
| Start and Completion of Consulting Services | PMU | 2019-08-01 | 2025-08-01 |  |  | Final Report by the Consultants
Building Constructions | Construction of new eligible Buildings | PMU | 2019-07-01 | 2020-03-01 |  |  | Letter of 50% commitment by State Govt. to JICA
| Letter on initiation of new building construction | JICA | 2019-09-01 | 2020-03-01 |  |  | No Objection by JICA
| Extension/ Renovation of existing eligible Buildings | PMU | 2019-07-01 | 2020-03-01 |  |  | Letter from PMU with proposal
| Letter on initiation of building extension/ renovation | JICA | 2019-09-01 | 2020-03-01 |  |  | No Objection by JICA
| Procurement of contractor(s) for construction of Buildings | PMU/ DMU | 2019-09-01 | 2020-03-01 |  |  | Tender document
Guidelines & Manuals | Hiring Experts for updating Operational Manual and Finance & Accounting Rules | PMU | 2018-12-01 | 2019-01-01 |  |  | Advertisement
| Review of Operational Manual and Finance & Accounting Rules | PMU | 2019-01-01 | 2019-03-01 |  |  | Document; Review by PMU
| Prepration of Operational Manual and Finance & Accounting Rules | PMU | 2018-10-01 | 2019-03-01 |  |  | Document; Approval by HPSC
| Guidelines and Manuals/ Handbook for Microplanning and Beat Forest Basic Plan | PMU | 2019-04-01 | 2019-06-01 |  |  | Guidelines/ Manuals
| Printing of Guidelines and Manuals/ Handbook after approval | PMU | 2019-07-01 | 2019-09-01 |  |  | Printing by PMU
| Guidelines for Procurement of Goods & Services under the project | PMU | 2019-04-01 | 2019-06-01 |  |  | Guidelines
| Printing of Guidelines for Procurement of Goods & Services after approval | PMU | 2019-07-01 | 2019-09-01 |  |  | Printing by PMU/ GB
| Guidelines for Buildings and Quality Assurance for constructions | PMU | 2019-04-01 | 2019-06-01 |  |  | Guidelines
| Printing of Guidelines for Buildings and Quality Assurance for constructions after approval | PMU | 2019-07-01 | 2019-09-01 |  |  | Printing by PMU/ GB
| Guidelines and Action Plan on Gender Mainstreaming | PMU | 2019-04-01 | 2019-06-01 |  |  | Guideline & Action Plan
| Printing of Guidelines and Action Plan on Gender Mainstreaming after approval | PMU | 2019-07-01 | 2019-09-01 |  |  | Printing & dissemination
| Printing of Guidelines for Environment and Social Considerations after approval | PMU | 2019-09-01 | 2019-10-01 |  |  | Printing by PMU/ GB
| Survey and Mapping of project areas | PMU/ DMU | 2019-07-01 | 2019-12-01 |  |  | Contract with Specialized Agency
| Demarcation of RoFR lands and JFM areas | SDMU/ RMU | 2019-07-01 | 2019-12-01
| Preparation of Beat Forest Basic Plan | SDMU/ RMU | 2019-10-01 | 2020-01-01 |  |  | Beat Forest Basic Plans
| Approval of Beat Forest Basic Plans | DMU/ PMU | 2019-12-01 | 2020-01-01 |  |  | Approval by DMU
| Nursery Establishment | DMU/ RMU | 2019-12-01 | 2020-05-01
| JFMC/ EDCs and RoFR Identification | DMU/ RMU | 2019-01-01 | 2019-06-01
| Community Mobilization | DMU/ RMU | 2019-01-01 | 2019-06-01
| Operationalization of community institutions - JFMCs/ EDCs and SHGs/ JLGs | DMU/ RMU | 2019-04-01 | 2019-06-01 |  |  | MoU
| Capacity Development of Community Institutions on Micro Planning | PMU/ DMU | 2019-07-01 | 2020-01-01
| Preparation of Micro Plans including Agro-Forestry/ Horticulture Plans | DMU/ RMU | 2020-02-01 | 2020-05-01 |  |  | Micro Plan
| Approval of Micro Plans including Agro-Forestry/ Horticulture Plans | DMU/ RMU | 2020-05-01 | 2020-07-01 |  |  | Approval by DMU/ PMU
| Entry Point Activity | DMU/ RMU | 2020-08-01 | 2020-12-01 |  |  | Letter of confirmation to JICA that all the works are fully completed
| Advance Work for plantation | RMU/ JFMC | 2020-12-01 | 2021-05-01
| Plantation and Maintenance | RMU/ JFMC | 2021-05-01 | 2024-08-01
| Completion Certificate for JFM Works | DMU/ RMU | 2024-09-01 | 2024-12-01 |  |  | Certificate
| Sustainability Plan | DMU/ PMU | 2025-01-01 | 2027-09-01 |  |  | Sustainability Plan Document
NCE | NTFP Resource Assesment at State level | PMU | 2019-02-01 | 2020-01-01 |  |  | Report
Phase 1 area support | Diagnostic Study for APU Creation | PMU | 2023-08-01 | 2023-12-01 |  |  | Report
| Action Plan for Phase 1 areas | PMU/ DMU | 2019-04-01 | 2019-09-01 |  |  | Action Plan and JICA's concurrence
Monitoring & Evaluation | Baseline Surveys - 1) Bio-physical, 2) Socio-economic | PMU | 2019-01-01 | 2019-06-01 |  |  | Baseline Report
| Mid-Term Impact Survey on 1) Bio-physical, 2) Socio-economic | PMU | 2023-01-01 | 2023-06-01 |  |  | Report
| End-Term Impact Survey on 1) Bio-physical, 2) Socio-economic | PMU | 2028-01-01 | 2028-06-01 |  |  | Report
Completion | Preparation for Project Completion Report | PMU | 2028-07-01 | 2028-10-01 |  |  | Project Completion Report
Note: The actions for each areas will be revised during the preparatory period of the Project